## Zend Bug Report
Swag Labs BUG REPORT
BUG ID |  |  |  | BUG OVERVIEW |  | ENVIRONMENT | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | Attachment | OPERATING SYSTEM | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | Relationship | SEVERITY | DEFECT PRIORITY | STATUS
BUG_001 | Checkout Completes with Empty Cart | Abdelrahman Ayman | 22/7/2025 | The system allows completing the checkout process even when the cart is empty. This behavior is incorrect as the cart should contain at least one item to proceed with the order. | https://drive.google.com/file/d/1lycDlqjHmP9J5Jzdwj-8mfAyLNHXKolN/view?usp=sharing | Windows 10 / Edge v138 | 1. Login with standard_user 2. Add item to cart 3. Navigate to cart 4. Remove the item 5. Proceed to checkout 6. Fill in personal info 7. Click Continue then Finish | Checkout should be blocked with a message like "Your cart is empty" or prevent reaching the final step. | Checkout completes and the message “Thank you for your order!” is shown, even though the cart is empty. | Showstopper | High | Dev Team | Open |  |  |  | Showstopper | Critical | Open
BUG_002 | System does not support increasing item quantity in cart | Abdelrahman Ayman | 22/7/2025 | After adding a product to the cart, the user has no option to increase the quantity of the same product. The cart only supports one unit per item without a "+" button or editable quantity field, which is not standard for e-commerce platforms. | https://drive.google.com/file/d/1434juLjCgfqt9mZpMM9rgZqaYh5ysEHi/view?usp=sharing | Windows 10 / Edge v138 | 1. Login. 2. Add any product to cart. 3. Go to cart. 4. Try to increase product quantity | Cart page should provide controls (e.g., "+" button, input field) to allow increasing item quantity. | No option exists to increase quantity of any product after adding it to cart. Only single quantity allowed. | Major | High | Dev Team | Open |  |  |  | Major | High | Resolved
[17 empty] | Minor | Medium | Closed
[17 empty] | Low | Low

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.